CONSTRUCTION BID PROPOSAL

──────────────────────────────────────────────────

Office Tenant Improvement — Suite 400

Project Information

Project:  Meridian Tower — Suite 400 Tenant Improvement

Location:  4800 N. Scottsdale Rd, Suite 400, Scottsdale, AZ 85251

Owner / Tenant:  Vanguard Professional Services, LLC

Architect:  Nelsen Partners (Phoenix)

Rentable Area:  12,500 SF (full floor)

Bid Number:  BC-2025-0714

Bid Date:  July 14, 2025

Bid Valid Through:  August 13, 2025 (30 calendar days)

General Contractor

Company:  Apex Commercial Builders, Inc.

Address:  1920 E. University Dr, Suite 110, Tempe, AZ 85281

License:  AZ ROC #245678 (B-1 Commercial)

Contact:  Marcus Delgado, VP of Preconstruction

Phone / Email:  (480) 555-0192  |  mdelgado@apexcb.com

Scope of Work Summary

Full interior demolition and build-out of a 12,500 SF office suite including open-plan workstations, six private offices, two conference rooms, a reception lobby, break room, server/IT closet, and restroom refresh. Work includes selective demo, steel framing, drywall, acoustical ceilings, flooring, doors & glazing, millwork, full MEP redistribution, fire sprinkler modifications, lighting, low-voltage rough-in, and finishes per the Construction Documents issued by Nelsen Partners dated June 10, 2025.

Detailed Cost Estimate

All pricing is based on plans and specifications dated June 10, 2025. Material pricing is subject to commodity escalation clauses noted in the Terms section.

| Description | Unit | Qty | Unit Cost | Total | Notes / Allowances |
| --- | --- | --- | --- | --- | --- |
| DIVISION 01 — GENERAL CONDITIONS |  |  |  |  |  |
| Subcontractor: Self-Performed (GC) |  |  |  |  |  |
| Project Management (12 wks) | LS | 1 | $18,000 | $18,000 |  |
| Temporary Facilities & Utilities | LS | 1 | $4,200 | $4,200 |  |
| Dumpster & Debris Removal | MO | 3 | $1,800 | $5,400 |  |
| Final Clean | SF | 12,500 | $0.35 | $4,375 |  |
| Permits & Inspections | LS | 1 | $6,500 | $6,500 |  |
| DIVISION 02 — SELECTIVE DEMOLITION |  |  |  |  |  |
| Subcontractor: Dozer Demolition LLC (Phoenix) |  |  |  |  |  |
| Remove existing partitions | SF | 4,200 | $2.80 | $11,760 |  |
| Remove ceiling grid & tiles | SF | 12,500 | $1.15 | $14,375 |  |
| Remove flooring (carpet/VCT) | SF | 12,500 | $0.95 | $11,875 |  |
| Patch & prep slab | SF | 12,500 | $0.60 | $7,500 |  |
| DIVISION 05 — METALS / STRUCTURAL |  |  |  |  |  |
| Subcontractor: Ironclad Steel Erectors (Tempe) |  |  |  |  |  |
| Light-gauge steel framing | SF | 6,800 | $4.25 | $28,900 |  |
| Miscellaneous steel (lintels, clips) | LS | 1 | $3,200 | $3,200 |  |
| DIVISION 06 — WOOD & PLASTICS |  |  |  |  |  |
| Subcontractor: Self-Performed (GC) |  |  |  |  |  |
| Wood blocking & backing | LF | 480 | $3.50 | $1,680 |  |
| Millwork — reception desk | LS | 1 | $14,500 | $14,500 |  |
| Millwork — break-room cabinetry | LS | 1 | $8,200 | $8,200 |  |
| DIVISION 07 — THERMAL & MOISTURE |  |  |  |  |  |
| Subcontractor: Desert Insulation Co. (Chandler) |  |  |  |  |  |
| Batt insulation (R-13 walls) | SF | 6,800 | $1.40 | $9,520 |  |
| Sound attenuation batts | SF | 2,400 | $1.85 | $4,440 |  |
| Firestopping / sealants | LS | 1 | $3,600 | $3,600 |  |
| DIVISION 08 — DOORS & GLAZING |  |  |  |  |  |
| Subcontractor: Arizona Door & Hardware (Scottsdale) |  |  |  |  |  |
| Interior wood doors w/ frames & hardware | EA | 28 | $1,150 | $32,200 |  |
| Glass storefront entry (lobby) | LS | 1 | $18,500 | $18,500 |  |
| Interior glass partitions (conf. rooms) | SF | 640 | $62 | $39,680 |  |
| Access control hardware allowance | LS | 1 | $8,000 | $8,000 |  |
| DIVISION 09 — FINISHES |  |  |  |  |  |
| Subcontractor: Multiple (see below) |  |  |  |  |  |
| Drywall — hang, tape, finish (Level 4) | SF | 28,000 | $2.45 | $68,600 |  |
| Drywall — Level 5 finish (exec. offices) | SF | 3,200 | $0.85 | $2,720 |  |
| Paint — walls (2 coats) | SF | 28,000 | $0.75 | $21,000 |  |
| Paint — accent walls | SF | 1,800 | $1.20 | $2,160 |  |
| Carpet tile (open office) | SF | 7,500 | $4.85 | $36,375 |  |
| LVP flooring (corridors & break room) | SF | 3,200 | $6.10 | $19,520 |  |
| Porcelain tile (restrooms) | SF | 1,800 | $12.50 | $22,500 |  |
| ACT ceiling grid & tiles (2×2) | SF | 10,000 | $3.25 | $32,500 |  |
| Drywall ceiling / soffits | SF | 2,500 | $5.60 | $14,000 |  |
| DIVISION 10 — SPECIALTIES |  |  |  |  |  |
| Subcontractor: Southwest Specialties Inc. (Mesa) |  |  |  |  |  |
| Toilet partitions & accessories | LS | 1 | $9,800 | $9,800 |  |
| Signage / wayfinding package | LS | 1 | $6,500 | $6,500 |  |
| Fire extinguisher cabinets | EA | 6 | $280 | $1,680 |  |
| DIVISION 15 — MECHANICAL (HVAC + PLUMBING) |  |  |  |  |  |
| Subcontractor: AirFlow Mechanical (Gilbert) |  |  |  |  |  |
| HVAC — VAV boxes & ductwork redistribution | LS | 1 | $68,000 | $68,000 |  |
| HVAC — controls / BMS tie-in | LS | 1 | $14,500 | $14,500 |  |
| Plumbing — break room sink & dishwasher | LS | 1 | $4,800 | $4,800 |  |
| Plumbing — restroom fixture relocation (6 ea) | EA | 6 | $2,200 | $13,200 |  |
| Fire sprinkler head relocation | EA | 42 | $185 | $7,770 |  |
| DIVISION 16 — ELECTRICAL |  |  |  |  |  |
| Subcontractor: Pinnacle Electric (Tempe) |  |  |  |  |  |
| Power distribution / panel upgrades | LS | 1 | $22,000 | $22,000 |  |
| Receptacles & circuits (general) | EA | 120 | $185 | $22,200 |  |
| Dedicated circuits (server/copy rooms) | EA | 8 | $650 | $5,200 |  |
| Lighting — LED 2×4 troffers | EA | 140 | $245 | $34,300 |  |
| Lighting — pendant / accent (lobby & conf.) | EA | 18 | $420 | $7,560 |  |
| Lighting controls / dimming / sensors | LS | 1 | $9,800 | $9,800 |  |
| Low-voltage rough-in (data/AV) | EA | 95 | $165 | $15,675 |  |
| Fire alarm device relocation | LS | 1 | $8,500 | $8,500 |  |
| DIRECT COST SUBTOTAL |  |  |  | $727,265 |  |
| Contingency (5%) |  |  |  | $36,363 | Unforeseen conditions |
| General Overhead (8%) |  |  |  | $58,181 |  |
| Profit (6%) |  |  |  | $43,636 |  |
| Payment & Performance Bond (1.5%) |  |  |  | $10,909 |  |
| TOTAL BID PRICE |  |  |  | $876,354 |  |

Preliminary Construction Schedule

Estimated duration: 15 weeks from Notice to Proceed. Schedule assumes timely owner decisions, no hazmat abatement, and permit issuance within 3 weeks of submission.

| Milestone | Target Date | Duration | Key Trades |
| --- | --- | --- | --- |
| Notice to Proceed | Aug 4, 2025 | — | — |
| Demolition Complete | Aug 18, 2025 | 2 weeks | Demo, Abatement |
| Rough-In Complete (MEP + Framing) | Sep 15, 2025 | 4 weeks | Mech, Elec, Steel |
| Drywall Close / Inspections | Sep 29, 2025 | 2 weeks | Drywall, Fire |
| Finishes (Floors, Paint, Ceilings) | Oct 20, 2025 | 3 weeks | Finishes subs |
| Doors, Specialties, Punch List | Nov 3, 2025 | 2 weeks | All trades |
| Substantial Completion | Nov 10, 2025 | — | — |
| Final Completion / Turnover | Nov 17, 2025 | 1 week | GC |

Clarifications & Assumptions

- Bid based on Construction Documents by Nelsen Partners dated 06/10/2025 (Sheets A1.0–A5.2, M1.0–M2.1, E1.0–E3.0).

- Building core/shell, elevators, base building HVAC equipment, and common-area finishes by landlord — not included in this bid.

- Normal business-hours work (7 AM – 5 PM, M–F). No overtime premium included.

- Owner to provide IT/data cabling, furniture, and AV equipment. GC provides conduit and low-voltage rough-in only.

- Hazardous material abatement (if any) excluded — pending Phase 1 report.

- Pricing assumes prevailing-wage rates are NOT required.

- Sales tax on materials included at current Maricopa County rate (8.6%).

Exclusions

- Furniture, fixtures & equipment (FF&E)

- IT / data cabling and termination

- Audio-visual equipment and installation

- Window treatments / blinds

- Security system (card readers, cameras) beyond rough-in

- Architectural and engineering fees

- Moving / relocation services

Terms & Conditions

- Payment terms: monthly progress billing, Net 30 days.

- Retainage: 5% held until Substantial Completion; released at Final Completion.

- Change orders priced at cost + 15% markup (10% overhead + 5% profit).

- Steel and copper subject to price escalation clause if NTP is issued more than 30 days after bid date.

- Warranty: 1-year standard workmanship warranty from date of Substantial Completion.

- Insurance: GC carries $2M General Liability, $1M Auto, Statutory Workers’ Comp, $5M Umbrella.

SUBMITTED BY

___________________________________

Marcus Delgado, VP of Preconstruction

Apex Commercial Builders, Inc.

Date: July 14, 2025

ACCEPTED BY (OWNER)

___________________________________

Authorized Representative

Vanguard Professional Services, LLC

Date: _____________